## Sheet1
Sprint Retrospective
| What went well | What went poorly | What ideas do you have | How should we take action
| This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
SPRINT 1 — SUMO Setup, Environment, Classical CV & Baseline (Weeks 1-6)
| Successfully built SUMO 4-arm intersection with all required files (nod, edg, con, tll, net, rou, cfg). TrafficEnv and ClassicalTrafficEnv implemented correctly with TraCI integration. HSV+contour detection reliably detects yellow SUMO vehicle sprites. Fixed-time baseline (Condition A) runs cleanly — results saved to JSON. SB3 wrapper works seamlessly with Gymnasium interface. | YOLOv8 was initially attempted for SUMO training — discovered SUMO sprites are 5-10px yellow triangles that YOLO cannot detect. Time was spent before reaching this conclusion. Initial ROI calibration was auto-calculated using equal image thirds — all vehicles fell into lane_1. Required rework. SUMO-GUI screenshots required pygetwindow and mss — platform-specific dependencies caused initial setup issues. | Build a dedicated ROI debug tool to visualise zone placement on actual screenshots before running full training. Add a smoke test mode to quickly validate environment setup (2-minute short run). Document YOLO rejection reason clearly in project context to avoid revisiting. | Created debug_roi.py to visualise ROI zones and iterated calibration. Added --timesteps and --eval-episodes flags for smoke testing. Project context document updated with YOLO rejection rationale and Classical CV decision.
SPRINT 2 — Full PPO Training, Evaluation, Real-World Validation & Review Prep (Weeks 7-12)
| PPO Condition C (Classical CV) trained successfully to 200k timesteps — achieved 97.2% waiting time reduction vs Fixed-Time baseline. real_data_demo.py pipeline working end-to-end: YOLO detects real vehicles, ROI zones count correctly, PPO makes decisions on real CCTV images. Built roi_calibrator.html — browser-based drag-to-draw tool generates pixel-precise get_rois() code, eliminating manual estimation errors. debug_roi.py refactored to import get_rois() from real_data_demo.py — single source of truth eliminates inconsistency bugs. All 4 evaluation charts generated. Live demo (record_demo.py) shows clear visual improvement. PPO made smarter decisions than fixed-time in 66.7% of 30 real CCTV images. | Three different real-world datasets were attempted before finding one that works: YouTube drone video (0 detections — moving camera), Pexels overhead video (YOLO can't detect overhead vehicles), Bellevue nighttime CCTV (1.70 avg detections — insufficient). ROI calibration required 3 iterations before achieving accurate zone placement on road areas. debug_roi.py and real_data_demo.py initially had inconsistent ROI values — caused confusing debug outputs. PPO agent selects NS-Turn 100% of the time on real images — reflects sim-to-real gap in policy transfer. Significant time spent investigating before confirming this is explainable behaviour, not a bug. max_steps inconsistency between conditions (A/B: 1000, C: 300) — known but not corrected to avoid invalidating existing trained models. | For future work: calibrate SUMO routes with real traffic flow data to reduce sim-to-real gap. Build an automated ROI validation step that checks vehicle detections per zone before running full demo. Add a SUMO_MAX auto-calibration feature that samples the training distribution to set the normalisation threshold automatically. Explore fine-tuning YOLOv8 on aerial/overhead traffic footage for overhead dataset compatibility. | Sim-to-real gap documented as future work with 3 clear solution pathways in project context. ROI calibrator tool built and integrated — future calibration can be done visually in under 5 minutes. Project context document updated with all design decisions, known issues, rejected approaches, and professor Q&A answers. PPO NS-Turn dominance explained and framed correctly for review: agent responds to real traffic conditions correctly — fixed-time ignores load entirely.